## Project Planner
Roobuck WiFi Wrist Tag
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 4 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Research localisation | 2 | 3 | 2 | 3 | 75%
Research power | 2 | 3 | 2 | 3 | 75%
Research client environment | 2 | 3 | 2 | 3 | 75%
Research casing materials | 2 | 3 | 2 | 3 | 75%
Compeditor analysis: localisation | 4 | 2 | 4 | 2 | 10%
Compeditor analysis: casing | 4 | 2 | 4 | 2 | 10%
Compeditor analysis: power | 4 | 2 | 4 | 2 | 10%
Project planinng: 1 | 4 | 1 | 4 | 1 | 50%
Conceptual design: localisation | 3 | 2 | 3 | 2 | 10%
Conceptual design: power | 3 | 2 | 3 | 2 | 10%
Conceptual design: casing | 3 | 2 | 3 | 2 | 10%
Report 1 write up 1 | 5 | 1 | 5 | 1 | 10%
Activity 13 | 9 | 6 | 9 | 7 | 50%
Activity 14 | 9 | 3 | 9 | 1 | 0%
Activity 15 | 9 | 4 | 8 | 5 | 1%
Activity 16 | 10 | 5 | 10 | 3 | 80%
Activity 17 | 11 | 2 | 11 | 5 | 0%
Activity 18 | 12 | 6 | 12 | 7 | 0%
Activity 19 | 12 | 1 | 12 | 5 | 0%
Activity 20 | 14 | 5 | 14 | 6 | 0%
Activity 21 | 14 | 8 | 14 | 2 | 44%
Activity 22 | 14 | 7 | 14 | 3 | 0%
Activity 23 | 15 | 4 | 15 | 8 | 12%
Activity 24 | 15 | 5 | 15 | 3 | 5%
Activity 25 | 15 | 8 | 15 | 5 | 0%
Activity 26 | 16 | 28 | 16 | 30 | 50%
Activity 27 | 1 | 1 | 1 | 1 | 0%
Activity 28 | 1 | 1 | 1 | 1 | 0%
Activity 29 | 1 | 1 | 1 | 1 | 0%
Activity 30 | 1 | 1 | 1 | 1 | 0%
Activity 31 | 1 | 1 | 1 | 1 | 0%
Activity 32 | 1 | 1 | 1 | 1 | 0%
Activity 33 | 1 | 1 | 1 | 1 | 0%
Activity 34 | 1 | 1 | 1 | 1 | 0%
Activity 35 | 1 | 1 | 1 | 1 | 0%
Activity 36 | 1 | 1 | 1 | 1 | 0%